## Overall
Falcon Portal cost estimate (synthetic sample)
All costs in USD. Cloud: Azure retail list prices in uaenorth fetched 2026-09-28, no discounts or reservations. Blue cells are inputs; black cells are formulas; green cells link to other sheets.
Inputs
Input | Value
Days of delivery (working days) | 84
Working days per month | 21
Months of delivery
Hours per month (always-on services) | 730
Delivery start date (optional; dates the epics and sprints) | 2026-03-02
Working days per sprint | 10
Years of run after go-live (3 to 5) | 5
Yearly increase in run costs | 3%
Run years, with the yearly increase
Contingency | 10%
Exchange rate (1 USD = x USD) | 1
Exchange rate for Claude prices (1 USD = x USD) | 1
Delivery team (build)
Role | Day rate (USD) | Employees | Days on delivery | Allocation | Mandays | Cost (USD) | Cited from
Project Manager |  | 1 |  | 50% |  |  | owner: Delivery Manager, 2026-09-28
Solution Architect |  | 1 | 20 | 100% |  |  | owner: Delivery Manager, 2026-09-28
Tech Lead |  | 1 |  | 100% |  |  | _bmad-output/planning-artifacts/architecture/falcon/ARCHITECTURE-SPINE.md AD-1
Developer |  | 3 |  | 100% |  |  | _bmad-output/specs/SPEC.md 3 Users
QA Engineer |  | 1 |  | 100% |  |  | owner: Delivery Manager, 2026-09-28
DevOps Engineer |  | 1 |  | 50% |  |  | _bmad-output/planning-artifacts/architecture/falcon/ARCHITECTURE-SPINE.md AD-1
Total
Run support (OPEX): IT support and maintenance after go-live
Role | Day rate (USD) | Mandays per year | Cost per year (USD) | Cited from
Developer |  | 60 |  | owner: Delivery Manager, 2026-09-28
DevOps Engineer |  | 24 |  | owner: Delivery Manager, 2026-09-28
QA Engineer |  | 12 |  | owner: Delivery Manager, 2026-09-28
Total
Cost summary
Item | Monthly (USD) | Months in delivery | Delivery cost (USD) | Run months per year | Run cost per year (USD) | Run cost over the horizon (USD) | Total (USD) | From
Dev environment |  |  |  | 12 |  |  |  | Dev sheet
Test environment |  | 2 |  | 12 |  |  |  | Test sheet
Prod environment |  | 1 |  | 12 |  |  |  | Prod sheet
Delivery team | [7 empty] | Delivery team table above
Run support (OPEX) | [7 empty] | Run support table above
Recurring run costs | [7 empty] | Run Costs sheet
Other one-off costs | [7 empty] | Other Costs sheet
Subtotal
Contingency
Grand total
Memo: Claude API usage at API list prices (not in the totals: Claude Code was on a subscription)

## Multi-Year
Multi-year view
In USD. Build is the delivery; each year after go-live carries the run costs, raised by the yearly increase, and the revenue given for it. Years past the horizon (Overall input) show zero. Contingency applies to every cost.
Category | Item | Build | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total
Revenue |  | 0
Revenue |  | 0
Revenue |  | 0
Revenue |  | 0
Cost | Build: delivery team, environments during delivery, one-off costs |  | 0 | 0 | 0 | 0 | 0
Cost | Dev environment (run) | 0
Cost | Test environment (run) | 0
Cost | Prod environment (run) | 0
Cost | Run support (OPEX) | 0
Cost | Recurring run costs | 0
Contingency | Contingency on every cost
Total revenue
Total costs
Net
Cumulative net
Payback
Return on cost (net / costs)

## Epics
Epics: deliverables, forecast and actual
In USD. Forecast: each epic takes a share of the build in proportion to its planned working days (that share of the delivery team and of the environments during delivery), plus the one-off costs tagged to it and its Claude API budget; dates run the epics one after another from the delivery start date. Actual: enter or keep the actual start and end dates; actual working days, the Claude API actual from the ledger, and team and infra scaled by actual / planned days (same team and rates) unless you enter the timesheet team cost. Blue cells are inputs; add an epic in a spare row.
Epic | Name | Deliverables | Planned days | Planned weeks | Planned start | Planned end | Share of build | Team mandays | Team cost (USD) | Infra cost (USD) | Other costs (USD) | Claude API budget (USD) | Forecast total (USD) | Actual start | Actual end | Actual days | Days variance | Days variance % | Claude API actual (USD) | Actual team cost, timesheets (USD) | Actual total (USD) | Cost variance (USD) | Cited from
1 | Customer onboarding | 1.1 Sign in with Entra ID 1.2 Start an application 1.3 Upload documents | 40 | [8 empty] | 150 |  | 2026-03-02 | 2026-04-20 | [7 empty] | _bmad-output/planning-artifacts/epics.md Epic 1: Customer onboarding
2 | Review and decision | 2.1 Review queue 2.2 Approve or reject 2.3 Notify the customer | 44 | [8 empty] | 150 |  | 2026-04-21 | 2026-06-26 | [7 empty] | _bmad-output/planning-artifacts/epics.md Epic 2: Review and decision
Total
Formulas:
Planned end = IF([Planned start]="","",WORKDAY([Planned start],[Planned days]-1))
Actual days = IF(OR([Planned days]="",[Actual start]="",[Actual end]=""),"",NETWORKDAYS([Actual start],[Actual end]))
Planned start = IF(OR([Planned days]="",ProjectStart=""),"",WORKDAY([Planned end, row above],1))

## Sprints
Sprints: forecast and actual
In USD. Every sprint is a timebox of the Overall input 'Working days per sprint' from the delivery start date. Forecast: the sprint's planned working days (the days of delivery, sprint by sprint) at the delivery team's and the environments' daily cost, plus any Claude API budget. Actual, up to the last actual activity (the latest completed story or day of Claude usage): the days worked in the sprint, the stories completed, the Claude API cost on its days, and the team at the days worked unless timesheets are entered. Sprints past the plan appear when work ran over. Blue cells are inputs.
Last actual activity
Sprint | Start | End | Planned days | Planned stories | Team cost (USD) | Infra cost (USD) | Claude API budget (USD) | Forecast total (USD) | Days worked | Stories done | Stories done (list) | Claude API actual (USD) | Actual team cost, timesheets (USD) | Actual total (USD) | Cost variance (USD)
1 |  |  |  | 1.1 Sign in with Entra ID
2 |  |  |  | 1.2 Start an application | [6 empty] | 1-1-sign-in
3 |  |  |  | 1.2 Start an application 1.3 Upload documents | [6 empty] | 1-2-start-application
4 |  |  |  | 1.3 Upload documents | [6 empty] | 1-3-upload-documents
5 |  |  |  | 2.1 Review queue
6 |  |  |  | 2.1 Review queue 2.2 Approve or reject | [6 empty] | 2-1-review-queue
7 |  |  |  | 2.2 Approve or reject | [6 empty] | 2-2-approve-or-reject
8 |  |  |  | 2.3 Notify the customer
9 |  |  |  | 2.3 Notify the customer | [6 empty] | 2-3-notify-customer
10
11
12
Total
Formulas:
Start = IF(OR([Planned days]="",ProjectStart=""),"",WORKDAY(ProjectStart,(1-1)*SprintDays))
End = IF([Start]="","",WORKDAY([Start],SprintDays-1))
Days worked = IF(OR([Start]="",LastActual="",[Start]>N(LastActual)),"",NETWORKDAYS([Start],MIN([End],LastActual)))

## Phase Budgets
Phase budgets: Claude API budget and actual per planning phase
In USD, at Claude API list prices. The budget each planning phase may spend (test design, governance, diagrams, course corrections ...), set once the epics and sprint plan are done; the epics and sprints carry their own budgets on their sheets. Actual: the phase's Claude cost from the ledger (Claude Usage Detail) once the close-out sheets are in. A control figure: not added to any total. Blue cells are inputs; name a phase as the token ledger does.
Phase | Claude API budget (USD) | Claude API actual (USD) | Variance (USD) | Variance % | Cited from
governance (Jules) | 40 |  |  |  | owner: Delivery Manager (synthetic), 2026-09-28
diagrams & design docs (Leonardo) | 25 |  |  |  | owner: Delivery Manager (synthetic), 2026-09-28
test design | 30 |  |  |  | owner: Delivery Manager (synthetic), 2026-09-28
Total

## Revenue
Revenue
Revenue the solution earns, per year after go-live, in USD, from the owner or the business case; each stream cites its source. Years past the horizon are ignored. Blue cells are inputs.
# | Stream | Basis | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Cited from | Note
1 | Application processing fees | $10 per application; 30,000 in year 1, +25% a year | 300000 | 375000 | 468750 | 585938 | 732422 | _bmad-output/specs/SPEC.md 7 Business case
Total

## Rate Card
Employee rate card
Day rates in USD. Source: Synthetic sample rates, not a real rate card; updated 2026-09-28. Blue cells are inputs; the team and support tables look roles up here.
Role | Day rate (USD) | Note
Project Manager | 760
Solution Architect | 950
Tech Lead | 870
Developer | 650
QA Engineer | 545
DevOps Engineer | 710

## Other Costs
Other one-off costs
Licences, tests, training and other one-off costs of the build, outside the environments and the team, in USD.
# | Item | Amount (USD) | Cited from | Note | Epic
1 | Penetration test | 12000 | owner: Security Lead, 2026-09-28 |  | 2
2 | GitHub Enterprise seats (12 months) | 8700 | assumption: 7 seats at list price
Total

## Run Costs
Recurring run costs (OPEX)
Yearly costs of running the solution outside the cloud environments and the support team: support contracts, licences, subscriptions. In USD per year; the Multi-Year sheet escalates them by the yearly increase.
# | Item | Annual cost (USD) | Cited from | Note
1 | Azure support plan (Standard) | 1200 | assumption: Standard support at list price
2 | GitHub Enterprise seats (4 for support) | 1000 | assumption: 4 seats at list price
Total

## Dev
Dev environment
Azure retail list prices (pay-as-you-go) in uaenorth, USD, fetched 2026-09-28. Daily cost is the monthly cost spread over the year (x 12 / 365). Blue cells are inputs.
# | Component | Azure service | SKU / tier | Unit | Unit price (USD) | Quantity | Usage per month | Monthly cost (USD) | Daily cost (USD) | Annual cost (USD) | Cited from | Price source | Note | Environment
1 | AKS nodes | Virtual Machines | Standard_D4s_v5 | 1 Hour | 0.235 | 2 | 220 |  |  |  | _bmad-output/planning-artifacts/architecture/falcon/ARCHITECTURE-SPINE.md AD-1 | Azure Retail Prices API, Virtual Machines Dsv5 Series / D4s v5, uaenorth, USD per 1 Hour, meterId 75a8da05-74dd-5b32-bb86-4f5cc74cdb60, fetched 2026-09-28 | Dev nodes stopped outside working hours | Dev
2 | Customer database | SQL Database | General Purpose Gen5, 2 vCore | 1 vCore Hour | 0.253 | 2 |  |  |  |  | _bmad-output/planning-artifacts/architecture/falcon/ARCHITECTURE-SPINE.md AD-2 | Synthetic sample price (not looked up) |  | Dev
3 | Document storage | Storage | Blob Hot LRS | 1 GB/Month | 0.019 | 50 | 1 |  |  |  | assumption: 50 GB of test documents | Synthetic sample price (not looked up) |  | Dev
4 | Secrets | Key Vault | Standard | 10K operations | 0.03 | 30 | 1 |  |  |  | _bmad-output/planning-artifacts/architecture/falcon/ARCHITECTURE-SPINE.md AD-5 | Synthetic sample price (not looked up) |  | Dev
5 | Logs and metrics | Log Analytics | Pay-as-you-go | 1 GB | 2.76 | 5 | 1 |  |  |  | _bmad-output/planning-artifacts/architecture/falcon/ARCHITECTURE-SPINE.md AD-5 | Synthetic sample price (not looked up) |  | Dev
Dev
Dev
Dev
Total

## Test
Test environment
Azure retail list prices (pay-as-you-go) in uaenorth, USD, fetched 2026-09-28. Daily cost is the monthly cost spread over the year (x 12 / 365). Blue cells are inputs.
# | Component | Azure service | SKU / tier | Unit | Unit price (USD) | Quantity | Usage per month | Monthly cost (USD) | Daily cost (USD) | Annual cost (USD) | Cited from | Price source | Note | Environment
1 | AKS nodes | Virtual Machines | Standard_D4s_v5 | 1 Hour | 0.235 | 2 |  |  |  |  | _bmad-output/planning-artifacts/architecture/falcon/ARCHITECTURE-SPINE.md AD-1 | Azure Retail Prices API, Virtual Machines Dsv5 Series / D4s v5, uaenorth, USD per 1 Hour, meterId 75a8da05-74dd-5b32-bb86-4f5cc74cdb60, fetched 2026-09-28 |  | Test
2 | Customer database | SQL Database | General Purpose Gen5, 2 vCore | 1 vCore Hour | 0.253 | 2 |  |  |  |  | _bmad-output/planning-artifacts/architecture/falcon/ARCHITECTURE-SPINE.md AD-2 | Synthetic sample price (not looked up) |  | Test
3 | Document storage | Storage | Blob Hot LRS | 1 GB/Month | 0.019 | 50 | 1 |  |  |  | assumption: 50 GB of test documents | Synthetic sample price (not looked up) |  | Test
4 | Secrets | Key Vault | Standard | 10K operations | 0.03 | 30 | 1 |  |  |  | _bmad-output/planning-artifacts/architecture/falcon/ARCHITECTURE-SPINE.md AD-5 | Synthetic sample price (not looked up) |  | Test
5 | Logs and metrics | Log Analytics | Pay-as-you-go | 1 GB | 2.76 | 5 | 1 |  |  |  | _bmad-output/planning-artifacts/architecture/falcon/ARCHITECTURE-SPINE.md AD-5 | Synthetic sample price (not looked up) |  | Test
6 | Edge | Azure Front Door Service | Standard base fee | 1 Month | 35 | 1 | 1 |  |  |  | _bmad-output/planning-artifacts/architecture/falcon/ARCHITECTURE-SPINE.md AD-4 | Synthetic sample price (not looked up) |  | Test
Test
Test
Test
Total

## Prod
Prod environment
Azure retail list prices (pay-as-you-go) in uaenorth, USD, fetched 2026-09-28. Daily cost is the monthly cost spread over the year (x 12 / 365). Blue cells are inputs.
# | Component | Azure service | SKU / tier | Unit | Unit price (USD) | Quantity | Usage per month | Monthly cost (USD) | Daily cost (USD) | Annual cost (USD) | Cited from | Price source | Note | Environment
1 | AKS nodes | Virtual Machines | Standard_D4s_v5 | 1 Hour | 0.235 | 3 |  |  |  |  | _bmad-output/planning-artifacts/architecture/falcon/ARCHITECTURE-SPINE.md AD-1 | Azure Retail Prices API, Virtual Machines Dsv5 Series / D4s v5, uaenorth, USD per 1 Hour, meterId 75a8da05-74dd-5b32-bb86-4f5cc74cdb60, fetched 2026-09-28 |  | Prod
2 | Customer database | SQL Database | General Purpose Gen5, 4 vCore | 1 vCore Hour | 0.253 | 4 |  |  |  |  | _bmad-output/planning-artifacts/architecture/falcon/ARCHITECTURE-SPINE.md AD-2 | Synthetic sample price (not looked up) |  | Prod
3 | Document storage | Storage | Blob Hot LRS | 1 GB/Month | 0.019 | 500 | 1 |  |  |  | _bmad-output/planning-artifacts/architecture/falcon/ARCHITECTURE-SPINE.md AD-3 | Synthetic sample price (not looked up) |  | Prod
4 | Secrets | Key Vault | Standard | 10K operations | 0.03 | 30 | 1 |  |  |  | _bmad-output/planning-artifacts/architecture/falcon/ARCHITECTURE-SPINE.md AD-5 | Synthetic sample price (not looked up) |  | Prod
5 | Logs and metrics | Log Analytics | Pay-as-you-go | 1 GB | 2.76 | 30 | 1 |  |  |  | _bmad-output/planning-artifacts/architecture/falcon/ARCHITECTURE-SPINE.md AD-5 | Synthetic sample price (not looked up) |  | Prod
6 | Edge | Azure Front Door Service | Standard base fee | 1 Month | 35 | 1 | 1 |  |  |  | _bmad-output/planning-artifacts/architecture/falcon/ARCHITECTURE-SPINE.md AD-4 | Synthetic sample price (not looked up) |  | Prod
Prod
Prod
Prod
Total

## Claude Prices
Claude API list prices
USD per million tokens, from https://platform.claude.com/docs/en/about-claude/pricing, read 2026-09-28. Blue cells are inputs.
Pricing model | Name | Input | Cache write 5m | Cache write 1h | Cache read | Output
claude-fable-5 | Claude Fable 5 | 10 | 12.5 | 20 | 1 | 50
claude-fable-5-1 | Claude Fable 5.1 | 10 | 12.5 | 20 | 0.25 | 50
claude-haiku-3-5 | Claude Haiku 3.5 | 0.8 | 1 | 1.6 | 0.08 | 4
claude-haiku-4-5 | Claude Haiku 4.5 | 1 | 1.25 | 2 | 0.1 | 5
claude-mythos-5 | Claude Mythos 5 | 10 | 12.5 | 20 | 1 | 50
claude-mythos-5-1 | Claude Mythos 5.1 | 10 | 12.5 | 20 | 0.25 | 50
claude-opus-4 | Claude Opus 4 | 15 | 18.75 | 30 | 1.5 | 75
claude-opus-4-1 | Claude Opus 4.1 | 15 | 18.75 | 30 | 1.5 | 75
claude-opus-4-5 | Claude Opus 4.5 | 5 | 6.25 | 10 | 0.5 | 25
claude-opus-4-6 | Claude Opus 4.6 | 5 | 6.25 | 10 | 0.5 | 25
claude-opus-4-7 | Claude Opus 4.7 | 5 | 6.25 | 10 | 0.5 | 25
claude-opus-4-8 | Claude Opus 4.8 | 5 | 6.25 | 10 | 0.5 | 25
claude-opus-5 | Claude Opus 5 | 5 | 6.25 | 10 | 0.5 | 25
claude-opus-5-5 | Claude Opus 5.5 | 4 | 5 | 8 | 0.2 | 20
claude-sonnet-4 | Claude Sonnet 4 | 3 | 3.75 | 6 | 0.3 | 15
claude-sonnet-4-5 | Claude Sonnet 4.5 | 3 | 3.75 | 6 | 0.3 | 15
claude-sonnet-4-6 | Claude Sonnet 4.6 | 3 | 3.75 | 6 | 0.3 | 15
claude-sonnet-5 | Claude Sonnet 5 | 2 | 2.5 | 4 | 0.2 | 10

## Claude Usage
Claude API usage
API calls and tokens counted from this project's Claude Code logs, costed at Claude API list prices. On a Pro, Max, Team or Enterprise subscription the bill is per seat: this is the API-equivalent cost.
Model | Calls | Input tokens | Cache write 5m tokens | Cache write 1h tokens | Cache read tokens | Output tokens | Cost (USD) | Cost (USD)
claude-haiku-4-5-20251001
claude-opus-5-5
claude-sonnet-5
Total

## Claude Usage Detail
Claude API calls by work item and model
From the token ledger (claude_usage.csv). Cost = tokens x the Claude Prices sheet; models with no price cost 0.
Kind | Work item | Story no | Title | Model | Pricing model | First call | Last call | Calls | Input tokens | Cache write 5m tokens | Cache write 1h tokens | Cache read tokens | Output tokens | Cost (USD) | Cost (USD)
planning | brainstorming |  |  | claude-opus-5-5 | claude-opus-5-5 | 2026-01-05 09:00 | 2026-01-05 17:00 | 42 | 9000 | 120000 | 380000 | 6100000 | 95000
planning | spec |  |  | claude-opus-5-5 | claude-opus-5-5 | 2026-01-06 09:00 | 2026-01-08 17:00 | 118 | 21000 | 300000 | 1250000 | 21400000 | 310000
planning | architecture |  |  | claude-opus-5-5 | claude-opus-5-5 | 2026-01-12 09:00 | 2026-01-22 17:00 | 356 | 64000 | 820000 | 3900000 | 68200000 | 905000
planning | UX design |  |  | claude-sonnet-5 | claude-sonnet-5 | 2026-01-19 09:00 | 2026-01-23 17:00 | 164 | 30000 | 410000 | 1500000 | 24800000 | 420000
planning | epics & stories |  |  | claude-sonnet-5 | claude-sonnet-5 | 2026-01-26 09:00 | 2026-01-27 17:00 | 97 | 18000 | 260000 | 900000 | 14600000 | 260000
planning | governance (Jules) |  |  | claude-opus-5-5 | claude-opus-5-5 | 2026-01-20 09:00 | 2026-02-20 17:00 | 88 | 15000 | 210000 | 760000 | 12500000 | 180000
planning | diagrams & design docs (Leonardo) |  |  | claude-opus-5-5 | claude-opus-5-5 | 2026-01-20 09:00 | 2026-01-22 17:00 | 61 | 11000 | 150000 | 520000 | 8700000 | 140000
story | FAL-11 | 1.1 | Sign in with Entra ID | claude-sonnet-5 | claude-sonnet-5 | 2026-03-02 09:00 | 2026-03-17 17:00 | 212 | 40000 | 500000 | 2100000 | 33900000 | 520000
story | FAL-12 | 1.2 | Start an application | claude-sonnet-5 | claude-sonnet-5 | 2026-03-18 09:00 | 2026-04-02 17:00 | 305 | 57000 | 720000 | 3000000 | 48700000 | 760000
story | FAL-13 | 1.3 | Upload documents | claude-sonnet-5 | claude-sonnet-5 | 2026-04-03 09:00 | 2026-04-20 17:00 | 248 | 46000 | 600000 | 2500000 | 40100000 | 610000
story | FAL-13 | 1.3 | Upload documents | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 2026-04-03 09:00 | 2026-04-20 17:00 | 96 | 18000 | 90000 | 300000 | 6200000 | 70000
story | FAL-21 | 2.1 | Review queue | claude-sonnet-5 | claude-sonnet-5 | 2026-04-21 09:00 | 2026-05-12 17:00 | 289 | 54000 | 690000 | 2900000 | 46300000 | 710000
story | FAL-22 | 2.2 | Approve or reject | claude-sonnet-5 | claude-sonnet-5 | 2026-05-13 09:00 | 2026-06-03 17:00 | 231 | 43000 | 560000 | 2300000 | 37000000 | 570000
story | FAL-23 | 2.3 | Notify the customer | claude-sonnet-5 | claude-sonnet-5 | 2026-06-04 09:00 | 2026-06-26 17:00 | 174 | 32000 | 420000 | 1700000 | 27800000 | 430000
ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 2026-03-02 09:00 | 2026-06-26 17:00 | 133 | 25000 | 110000 | 420000 | 8600000 | 95000

## Claude Usage Daily
Claude API usage by day
From the token ledger (claude_usage_daily.csv, refreshed after every turn). Cost = tokens x the Claude Prices sheet; models with no price cost 0.
Day | Kind | Work item | Story no | Title | Model | Pricing model | Calls | Input tokens | Cache write 5m tokens | Cache write 1h tokens | Cache read tokens | Output tokens | Cost (USD) | Cost (USD)
2026-01-05 | planning | brainstorming |  |  | claude-opus-5-5 | claude-opus-5-5 | 42 | 9000 | 120000 | 380000 | 6100000 | 95000
2026-01-06 | planning | spec |  |  | claude-opus-5-5 | claude-opus-5-5 | 39 | 7000 | 100000 | 416666 | 7133333 | 103333
2026-01-07 | planning | spec |  |  | claude-opus-5-5 | claude-opus-5-5 | 39 | 7000 | 100000 | 416666 | 7133333 | 103333
2026-01-08 | planning | spec |  |  | claude-opus-5-5 | claude-opus-5-5 | 40 | 7000 | 100000 | 416668 | 7133334 | 103334
2026-01-12 | planning | architecture |  |  | claude-opus-5-5 | claude-opus-5-5 | 39 | 7111 | 91111 | 433333 | 7577777 | 100555
2026-01-13 | planning | architecture |  |  | claude-opus-5-5 | claude-opus-5-5 | 39 | 7111 | 91111 | 433333 | 7577777 | 100555
2026-01-14 | planning | architecture |  |  | claude-opus-5-5 | claude-opus-5-5 | 39 | 7111 | 91111 | 433333 | 7577777 | 100555
2026-01-15 | planning | architecture |  |  | claude-opus-5-5 | claude-opus-5-5 | 39 | 7111 | 91111 | 433333 | 7577777 | 100555
2026-01-16 | planning | architecture |  |  | claude-opus-5-5 | claude-opus-5-5 | 39 | 7111 | 91111 | 433333 | 7577777 | 100555
2026-01-19 | planning | UX design |  |  | claude-sonnet-5 | claude-sonnet-5 | 32 | 6000 | 82000 | 300000 | 4960000 | 84000
2026-01-19 | planning | architecture |  |  | claude-opus-5-5 | claude-opus-5-5 | 39 | 7111 | 91111 | 433333 | 7577777 | 100555
2026-01-20 | planning | UX design |  |  | claude-sonnet-5 | claude-sonnet-5 | 32 | 6000 | 82000 | 300000 | 4960000 | 84000
2026-01-20 | planning | architecture |  |  | claude-opus-5-5 | claude-opus-5-5 | 39 | 7111 | 91111 | 433333 | 7577777 | 100555
2026-01-20 | planning | diagrams & design docs (Leonardo) |  |  | claude-opus-5-5 | claude-opus-5-5 | 20 | 3666 | 50000 | 173333 | 2900000 | 46666
2026-01-20 | planning | governance (Jules) |  |  | claude-opus-5-5 | claude-opus-5-5 | 3 | 625 | 8750 | 31666 | 520833 | 7500
2026-01-21 | planning | UX design |  |  | claude-sonnet-5 | claude-sonnet-5 | 32 | 6000 | 82000 | 300000 | 4960000 | 84000
2026-01-21 | planning | architecture |  |  | claude-opus-5-5 | claude-opus-5-5 | 39 | 7111 | 91111 | 433333 | 7577777 | 100555
2026-01-21 | planning | diagrams & design docs (Leonardo) |  |  | claude-opus-5-5 | claude-opus-5-5 | 20 | 3666 | 50000 | 173333 | 2900000 | 46666
2026-01-21 | planning | governance (Jules) |  |  | claude-opus-5-5 | claude-opus-5-5 | 3 | 625 | 8750 | 31666 | 520833 | 7500
2026-01-22 | planning | UX design |  |  | claude-sonnet-5 | claude-sonnet-5 | 32 | 6000 | 82000 | 300000 | 4960000 | 84000
2026-01-22 | planning | architecture |  |  | claude-opus-5-5 | claude-opus-5-5 | 44 | 7112 | 91112 | 433336 | 7577784 | 100560
2026-01-22 | planning | diagrams & design docs (Leonardo) |  |  | claude-opus-5-5 | claude-opus-5-5 | 21 | 3668 | 50000 | 173334 | 2900000 | 46668
2026-01-22 | planning | governance (Jules) |  |  | claude-opus-5-5 | claude-opus-5-5 | 3 | 625 | 8750 | 31666 | 520833 | 7500
2026-01-23 | planning | UX design |  |  | claude-sonnet-5 | claude-sonnet-5 | 36 | 6000 | 82000 | 300000 | 4960000 | 84000
2026-01-23 | planning | governance (Jules) |  |  | claude-opus-5-5 | claude-opus-5-5 | 3 | 625 | 8750 | 31666 | 520833 | 7500
2026-01-26 | planning | epics & stories |  |  | claude-sonnet-5 | claude-sonnet-5 | 48 | 9000 | 130000 | 450000 | 7300000 | 130000
2026-01-26 | planning | governance (Jules) |  |  | claude-opus-5-5 | claude-opus-5-5 | 3 | 625 | 8750 | 31666 | 520833 | 7500
2026-01-27 | planning | epics & stories |  |  | claude-sonnet-5 | claude-sonnet-5 | 49 | 9000 | 130000 | 450000 | 7300000 | 130000
2026-01-27 | planning | governance (Jules) |  |  | claude-opus-5-5 | claude-opus-5-5 | 3 | 625 | 8750 | 31666 | 520833 | 7500
2026-01-28 | planning | governance (Jules) |  |  | claude-opus-5-5 | claude-opus-5-5 | 3 | 625 | 8750 | 31666 | 520833 | 7500
2026-01-29 | planning | governance (Jules) |  |  | claude-opus-5-5 | claude-opus-5-5 | 3 | 625 | 8750 | 31666 | 520833 | 7500
2026-01-30 | planning | governance (Jules) |  |  | claude-opus-5-5 | claude-opus-5-5 | 3 | 625 | 8750 | 31666 | 520833 | 7500
2026-02-02 | planning | governance (Jules) |  |  | claude-opus-5-5 | claude-opus-5-5 | 3 | 625 | 8750 | 31666 | 520833 | 7500
2026-02-03 | planning | governance (Jules) |  |  | claude-opus-5-5 | claude-opus-5-5 | 3 | 625 | 8750 | 31666 | 520833 | 7500
2026-02-04 | planning | governance (Jules) |  |  | claude-opus-5-5 | claude-opus-5-5 | 3 | 625 | 8750 | 31666 | 520833 | 7500
2026-02-05 | planning | governance (Jules) |  |  | claude-opus-5-5 | claude-opus-5-5 | 3 | 625 | 8750 | 31666 | 520833 | 7500
2026-02-06 | planning | governance (Jules) |  |  | claude-opus-5-5 | claude-opus-5-5 | 3 | 625 | 8750 | 31666 | 520833 | 7500
2026-02-09 | planning | governance (Jules) |  |  | claude-opus-5-5 | claude-opus-5-5 | 3 | 625 | 8750 | 31666 | 520833 | 7500
2026-02-10 | planning | governance (Jules) |  |  | claude-opus-5-5 | claude-opus-5-5 | 3 | 625 | 8750 | 31666 | 520833 | 7500
2026-02-11 | planning | governance (Jules) |  |  | claude-opus-5-5 | claude-opus-5-5 | 3 | 625 | 8750 | 31666 | 520833 | 7500
2026-02-12 | planning | governance (Jules) |  |  | claude-opus-5-5 | claude-opus-5-5 | 3 | 625 | 8750 | 31666 | 520833 | 7500
2026-02-13 | planning | governance (Jules) |  |  | claude-opus-5-5 | claude-opus-5-5 | 3 | 625 | 8750 | 31666 | 520833 | 7500
2026-02-16 | planning | governance (Jules) |  |  | claude-opus-5-5 | claude-opus-5-5 | 3 | 625 | 8750 | 31666 | 520833 | 7500
2026-02-17 | planning | governance (Jules) |  |  | claude-opus-5-5 | claude-opus-5-5 | 3 | 625 | 8750 | 31666 | 520833 | 7500
2026-02-18 | planning | governance (Jules) |  |  | claude-opus-5-5 | claude-opus-5-5 | 3 | 625 | 8750 | 31666 | 520833 | 7500
2026-02-19 | planning | governance (Jules) |  |  | claude-opus-5-5 | claude-opus-5-5 | 3 | 625 | 8750 | 31666 | 520833 | 7500
2026-02-20 | planning | governance (Jules) |  |  | claude-opus-5-5 | claude-opus-5-5 | 19 | 625 | 8750 | 31682 | 520841 | 7500
2026-03-02 | story | FAL-11 | 1.1 | Sign in with Entra ID | claude-sonnet-5 | claude-sonnet-5 | 17 | 3333 | 41666 | 175000 | 2825000 | 43333
2026-03-02 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-03-03 | story | FAL-11 | 1.1 | Sign in with Entra ID | claude-sonnet-5 | claude-sonnet-5 | 17 | 3333 | 41666 | 175000 | 2825000 | 43333
2026-03-03 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-03-04 | story | FAL-11 | 1.1 | Sign in with Entra ID | claude-sonnet-5 | claude-sonnet-5 | 17 | 3333 | 41666 | 175000 | 2825000 | 43333
2026-03-04 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-03-05 | story | FAL-11 | 1.1 | Sign in with Entra ID | claude-sonnet-5 | claude-sonnet-5 | 17 | 3333 | 41666 | 175000 | 2825000 | 43333
2026-03-05 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-03-06 | story | FAL-11 | 1.1 | Sign in with Entra ID | claude-sonnet-5 | claude-sonnet-5 | 17 | 3333 | 41666 | 175000 | 2825000 | 43333
2026-03-06 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-03-09 | story | FAL-11 | 1.1 | Sign in with Entra ID | claude-sonnet-5 | claude-sonnet-5 | 17 | 3333 | 41666 | 175000 | 2825000 | 43333
2026-03-09 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-03-10 | story | FAL-11 | 1.1 | Sign in with Entra ID | claude-sonnet-5 | claude-sonnet-5 | 17 | 3333 | 41666 | 175000 | 2825000 | 43333
2026-03-10 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-03-11 | story | FAL-11 | 1.1 | Sign in with Entra ID | claude-sonnet-5 | claude-sonnet-5 | 17 | 3333 | 41666 | 175000 | 2825000 | 43333
2026-03-11 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-03-12 | story | FAL-11 | 1.1 | Sign in with Entra ID | claude-sonnet-5 | claude-sonnet-5 | 17 | 3333 | 41666 | 175000 | 2825000 | 43333
2026-03-12 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-03-13 | story | FAL-11 | 1.1 | Sign in with Entra ID | claude-sonnet-5 | claude-sonnet-5 | 17 | 3333 | 41666 | 175000 | 2825000 | 43333
2026-03-13 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-03-16 | story | FAL-11 | 1.1 | Sign in with Entra ID | claude-sonnet-5 | claude-sonnet-5 | 17 | 3333 | 41666 | 175000 | 2825000 | 43333
2026-03-16 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-03-17 | story | FAL-11 | 1.1 | Sign in with Entra ID | claude-sonnet-5 | claude-sonnet-5 | 25 | 3337 | 41674 | 175000 | 2825000 | 43337
2026-03-17 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-03-18 | story | FAL-12 | 1.2 | Start an application | claude-sonnet-5 | claude-sonnet-5 | 25 | 4750 | 60000 | 250000 | 4058333 | 63333
2026-03-18 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-03-19 | story | FAL-12 | 1.2 | Start an application | claude-sonnet-5 | claude-sonnet-5 | 25 | 4750 | 60000 | 250000 | 4058333 | 63333
2026-03-19 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-03-20 | story | FAL-12 | 1.2 | Start an application | claude-sonnet-5 | claude-sonnet-5 | 25 | 4750 | 60000 | 250000 | 4058333 | 63333
2026-03-20 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-03-23 | story | FAL-12 | 1.2 | Start an application | claude-sonnet-5 | claude-sonnet-5 | 25 | 4750 | 60000 | 250000 | 4058333 | 63333
2026-03-23 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-03-24 | story | FAL-12 | 1.2 | Start an application | claude-sonnet-5 | claude-sonnet-5 | 25 | 4750 | 60000 | 250000 | 4058333 | 63333
2026-03-24 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-03-25 | story | FAL-12 | 1.2 | Start an application | claude-sonnet-5 | claude-sonnet-5 | 25 | 4750 | 60000 | 250000 | 4058333 | 63333
2026-03-25 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-03-26 | story | FAL-12 | 1.2 | Start an application | claude-sonnet-5 | claude-sonnet-5 | 25 | 4750 | 60000 | 250000 | 4058333 | 63333
2026-03-26 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-03-27 | story | FAL-12 | 1.2 | Start an application | claude-sonnet-5 | claude-sonnet-5 | 25 | 4750 | 60000 | 250000 | 4058333 | 63333
2026-03-27 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-03-30 | story | FAL-12 | 1.2 | Start an application | claude-sonnet-5 | claude-sonnet-5 | 25 | 4750 | 60000 | 250000 | 4058333 | 63333
2026-03-30 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-03-31 | story | FAL-12 | 1.2 | Start an application | claude-sonnet-5 | claude-sonnet-5 | 25 | 4750 | 60000 | 250000 | 4058333 | 63333
2026-03-31 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-04-01 | story | FAL-12 | 1.2 | Start an application | claude-sonnet-5 | claude-sonnet-5 | 25 | 4750 | 60000 | 250000 | 4058333 | 63333
2026-04-01 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-04-02 | story | FAL-12 | 1.2 | Start an application | claude-sonnet-5 | claude-sonnet-5 | 30 | 4750 | 60000 | 250000 | 4058337 | 63337
2026-04-02 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-04-03 | story | FAL-13 | 1.3 | Upload documents | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 8 | 1500 | 7500 | 25000 | 516666 | 5833
2026-04-03 | story | FAL-13 | 1.3 | Upload documents | claude-sonnet-5 | claude-sonnet-5 | 20 | 3833 | 50000 | 208333 | 3341666 | 50833
2026-04-03 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-04-06 | story | FAL-13 | 1.3 | Upload documents | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 8 | 1500 | 7500 | 25000 | 516666 | 5833
2026-04-06 | story | FAL-13 | 1.3 | Upload documents | claude-sonnet-5 | claude-sonnet-5 | 20 | 3833 | 50000 | 208333 | 3341666 | 50833
2026-04-06 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-04-07 | story | FAL-13 | 1.3 | Upload documents | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 8 | 1500 | 7500 | 25000 | 516666 | 5833
2026-04-07 | story | FAL-13 | 1.3 | Upload documents | claude-sonnet-5 | claude-sonnet-5 | 20 | 3833 | 50000 | 208333 | 3341666 | 50833
2026-04-07 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-04-08 | story | FAL-13 | 1.3 | Upload documents | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 8 | 1500 | 7500 | 25000 | 516666 | 5833
2026-04-08 | story | FAL-13 | 1.3 | Upload documents | claude-sonnet-5 | claude-sonnet-5 | 20 | 3833 | 50000 | 208333 | 3341666 | 50833
2026-04-08 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-04-09 | story | FAL-13 | 1.3 | Upload documents | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 8 | 1500 | 7500 | 25000 | 516666 | 5833
2026-04-09 | story | FAL-13 | 1.3 | Upload documents | claude-sonnet-5 | claude-sonnet-5 | 20 | 3833 | 50000 | 208333 | 3341666 | 50833
2026-04-09 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-04-10 | story | FAL-13 | 1.3 | Upload documents | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 8 | 1500 | 7500 | 25000 | 516666 | 5833
2026-04-10 | story | FAL-13 | 1.3 | Upload documents | claude-sonnet-5 | claude-sonnet-5 | 20 | 3833 | 50000 | 208333 | 3341666 | 50833
2026-04-10 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-04-13 | story | FAL-13 | 1.3 | Upload documents | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 8 | 1500 | 7500 | 25000 | 516666 | 5833
2026-04-13 | story | FAL-13 | 1.3 | Upload documents | claude-sonnet-5 | claude-sonnet-5 | 20 | 3833 | 50000 | 208333 | 3341666 | 50833
2026-04-13 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-04-14 | story | FAL-13 | 1.3 | Upload documents | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 8 | 1500 | 7500 | 25000 | 516666 | 5833
2026-04-14 | story | FAL-13 | 1.3 | Upload documents | claude-sonnet-5 | claude-sonnet-5 | 20 | 3833 | 50000 | 208333 | 3341666 | 50833
2026-04-14 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-04-15 | story | FAL-13 | 1.3 | Upload documents | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 8 | 1500 | 7500 | 25000 | 516666 | 5833
2026-04-15 | story | FAL-13 | 1.3 | Upload documents | claude-sonnet-5 | claude-sonnet-5 | 20 | 3833 | 50000 | 208333 | 3341666 | 50833
2026-04-15 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-04-16 | story | FAL-13 | 1.3 | Upload documents | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 8 | 1500 | 7500 | 25000 | 516666 | 5833
2026-04-16 | story | FAL-13 | 1.3 | Upload documents | claude-sonnet-5 | claude-sonnet-5 | 20 | 3833 | 50000 | 208333 | 3341666 | 50833
2026-04-16 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-04-17 | story | FAL-13 | 1.3 | Upload documents | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 8 | 1500 | 7500 | 25000 | 516666 | 5833
2026-04-17 | story | FAL-13 | 1.3 | Upload documents | claude-sonnet-5 | claude-sonnet-5 | 20 | 3833 | 50000 | 208333 | 3341666 | 50833
2026-04-17 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-04-20 | story | FAL-13 | 1.3 | Upload documents | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 8 | 1500 | 7500 | 25000 | 516674 | 5837
2026-04-20 | story | FAL-13 | 1.3 | Upload documents | claude-sonnet-5 | claude-sonnet-5 | 28 | 3837 | 50000 | 208337 | 3341674 | 50837
2026-04-20 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-04-21 | story | FAL-21 | 2.1 | Review queue | claude-sonnet-5 | claude-sonnet-5 | 18 | 3375 | 43125 | 181250 | 2893750 | 44375
2026-04-21 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-04-22 | story | FAL-21 | 2.1 | Review queue | claude-sonnet-5 | claude-sonnet-5 | 18 | 3375 | 43125 | 181250 | 2893750 | 44375
2026-04-22 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-04-23 | story | FAL-21 | 2.1 | Review queue | claude-sonnet-5 | claude-sonnet-5 | 18 | 3375 | 43125 | 181250 | 2893750 | 44375
2026-04-23 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-04-24 | story | FAL-21 | 2.1 | Review queue | claude-sonnet-5 | claude-sonnet-5 | 18 | 3375 | 43125 | 181250 | 2893750 | 44375
2026-04-24 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-04-27 | story | FAL-21 | 2.1 | Review queue | claude-sonnet-5 | claude-sonnet-5 | 18 | 3375 | 43125 | 181250 | 2893750 | 44375
2026-04-27 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-04-28 | story | FAL-21 | 2.1 | Review queue | claude-sonnet-5 | claude-sonnet-5 | 18 | 3375 | 43125 | 181250 | 2893750 | 44375
2026-04-28 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-04-29 | story | FAL-21 | 2.1 | Review queue | claude-sonnet-5 | claude-sonnet-5 | 18 | 3375 | 43125 | 181250 | 2893750 | 44375
2026-04-29 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-04-30 | story | FAL-21 | 2.1 | Review queue | claude-sonnet-5 | claude-sonnet-5 | 18 | 3375 | 43125 | 181250 | 2893750 | 44375
2026-04-30 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-05-01 | story | FAL-21 | 2.1 | Review queue | claude-sonnet-5 | claude-sonnet-5 | 18 | 3375 | 43125 | 181250 | 2893750 | 44375
2026-05-01 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-05-04 | story | FAL-21 | 2.1 | Review queue | claude-sonnet-5 | claude-sonnet-5 | 18 | 3375 | 43125 | 181250 | 2893750 | 44375
2026-05-04 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-05-05 | story | FAL-21 | 2.1 | Review queue | claude-sonnet-5 | claude-sonnet-5 | 18 | 3375 | 43125 | 181250 | 2893750 | 44375
2026-05-05 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-05-06 | story | FAL-21 | 2.1 | Review queue | claude-sonnet-5 | claude-sonnet-5 | 18 | 3375 | 43125 | 181250 | 2893750 | 44375
2026-05-06 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-05-07 | story | FAL-21 | 2.1 | Review queue | claude-sonnet-5 | claude-sonnet-5 | 18 | 3375 | 43125 | 181250 | 2893750 | 44375
2026-05-07 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-05-08 | story | FAL-21 | 2.1 | Review queue | claude-sonnet-5 | claude-sonnet-5 | 18 | 3375 | 43125 | 181250 | 2893750 | 44375
2026-05-08 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-05-11 | story | FAL-21 | 2.1 | Review queue | claude-sonnet-5 | claude-sonnet-5 | 18 | 3375 | 43125 | 181250 | 2893750 | 44375
2026-05-11 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-05-12 | story | FAL-21 | 2.1 | Review queue | claude-sonnet-5 | claude-sonnet-5 | 19 | 3375 | 43125 | 181250 | 2893750 | 44375
2026-05-12 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-05-13 | story | FAL-22 | 2.2 | Approve or reject | claude-sonnet-5 | claude-sonnet-5 | 14 | 2687 | 35000 | 143750 | 2312500 | 35625
2026-05-13 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-05-14 | story | FAL-22 | 2.2 | Approve or reject | claude-sonnet-5 | claude-sonnet-5 | 14 | 2687 | 35000 | 143750 | 2312500 | 35625
2026-05-14 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-05-15 | story | FAL-22 | 2.2 | Approve or reject | claude-sonnet-5 | claude-sonnet-5 | 14 | 2687 | 35000 | 143750 | 2312500 | 35625
2026-05-15 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-05-18 | story | FAL-22 | 2.2 | Approve or reject | claude-sonnet-5 | claude-sonnet-5 | 14 | 2687 | 35000 | 143750 | 2312500 | 35625
2026-05-18 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-05-19 | story | FAL-22 | 2.2 | Approve or reject | claude-sonnet-5 | claude-sonnet-5 | 14 | 2687 | 35000 | 143750 | 2312500 | 35625
2026-05-19 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-05-20 | story | FAL-22 | 2.2 | Approve or reject | claude-sonnet-5 | claude-sonnet-5 | 14 | 2687 | 35000 | 143750 | 2312500 | 35625
2026-05-20 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-05-21 | story | FAL-22 | 2.2 | Approve or reject | claude-sonnet-5 | claude-sonnet-5 | 14 | 2687 | 35000 | 143750 | 2312500 | 35625
2026-05-21 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-05-22 | story | FAL-22 | 2.2 | Approve or reject | claude-sonnet-5 | claude-sonnet-5 | 14 | 2687 | 35000 | 143750 | 2312500 | 35625
2026-05-22 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-05-25 | story | FAL-22 | 2.2 | Approve or reject | claude-sonnet-5 | claude-sonnet-5 | 14 | 2687 | 35000 | 143750 | 2312500 | 35625
2026-05-25 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-05-26 | story | FAL-22 | 2.2 | Approve or reject | claude-sonnet-5 | claude-sonnet-5 | 14 | 2687 | 35000 | 143750 | 2312500 | 35625
2026-05-26 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-05-27 | story | FAL-22 | 2.2 | Approve or reject | claude-sonnet-5 | claude-sonnet-5 | 14 | 2687 | 35000 | 143750 | 2312500 | 35625
2026-05-27 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-05-28 | story | FAL-22 | 2.2 | Approve or reject | claude-sonnet-5 | claude-sonnet-5 | 14 | 2687 | 35000 | 143750 | 2312500 | 35625
2026-05-28 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-05-29 | story | FAL-22 | 2.2 | Approve or reject | claude-sonnet-5 | claude-sonnet-5 | 14 | 2687 | 35000 | 143750 | 2312500 | 35625
2026-05-29 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-06-01 | story | FAL-22 | 2.2 | Approve or reject | claude-sonnet-5 | claude-sonnet-5 | 14 | 2687 | 35000 | 143750 | 2312500 | 35625
2026-06-01 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-06-02 | story | FAL-22 | 2.2 | Approve or reject | claude-sonnet-5 | claude-sonnet-5 | 14 | 2687 | 35000 | 143750 | 2312500 | 35625
2026-06-02 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-06-03 | story | FAL-22 | 2.2 | Approve or reject | claude-sonnet-5 | claude-sonnet-5 | 21 | 2695 | 35000 | 143750 | 2312500 | 35625
2026-06-03 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-06-04 | story | FAL-23 | 2.3 | Notify the customer | claude-sonnet-5 | claude-sonnet-5 | 10 | 1882 | 24705 | 100000 | 1635294 | 25294
2026-06-04 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-06-05 | story | FAL-23 | 2.3 | Notify the customer | claude-sonnet-5 | claude-sonnet-5 | 10 | 1882 | 24705 | 100000 | 1635294 | 25294
2026-06-05 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-06-08 | story | FAL-23 | 2.3 | Notify the customer | claude-sonnet-5 | claude-sonnet-5 | 10 | 1882 | 24705 | 100000 | 1635294 | 25294
2026-06-08 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-06-09 | story | FAL-23 | 2.3 | Notify the customer | claude-sonnet-5 | claude-sonnet-5 | 10 | 1882 | 24705 | 100000 | 1635294 | 25294
2026-06-09 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-06-10 | story | FAL-23 | 2.3 | Notify the customer | claude-sonnet-5 | claude-sonnet-5 | 10 | 1882 | 24705 | 100000 | 1635294 | 25294
2026-06-10 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-06-11 | story | FAL-23 | 2.3 | Notify the customer | claude-sonnet-5 | claude-sonnet-5 | 10 | 1882 | 24705 | 100000 | 1635294 | 25294
2026-06-11 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-06-12 | story | FAL-23 | 2.3 | Notify the customer | claude-sonnet-5 | claude-sonnet-5 | 10 | 1882 | 24705 | 100000 | 1635294 | 25294
2026-06-12 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-06-15 | story | FAL-23 | 2.3 | Notify the customer | claude-sonnet-5 | claude-sonnet-5 | 10 | 1882 | 24705 | 100000 | 1635294 | 25294
2026-06-15 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-06-16 | story | FAL-23 | 2.3 | Notify the customer | claude-sonnet-5 | claude-sonnet-5 | 10 | 1882 | 24705 | 100000 | 1635294 | 25294
2026-06-16 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-06-17 | story | FAL-23 | 2.3 | Notify the customer | claude-sonnet-5 | claude-sonnet-5 | 10 | 1882 | 24705 | 100000 | 1635294 | 25294
2026-06-17 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-06-18 | story | FAL-23 | 2.3 | Notify the customer | claude-sonnet-5 | claude-sonnet-5 | 10 | 1882 | 24705 | 100000 | 1635294 | 25294
2026-06-18 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-06-19 | story | FAL-23 | 2.3 | Notify the customer | claude-sonnet-5 | claude-sonnet-5 | 10 | 1882 | 24705 | 100000 | 1635294 | 25294
2026-06-19 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-06-22 | story | FAL-23 | 2.3 | Notify the customer | claude-sonnet-5 | claude-sonnet-5 | 10 | 1882 | 24705 | 100000 | 1635294 | 25294
2026-06-22 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-06-23 | story | FAL-23 | 2.3 | Notify the customer | claude-sonnet-5 | claude-sonnet-5 | 10 | 1882 | 24705 | 100000 | 1635294 | 25294
2026-06-23 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-06-24 | story | FAL-23 | 2.3 | Notify the customer | claude-sonnet-5 | claude-sonnet-5 | 10 | 1882 | 24705 | 100000 | 1635294 | 25294
2026-06-24 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-06-25 | story | FAL-23 | 2.3 | Notify the customer | claude-sonnet-5 | claude-sonnet-5 | 10 | 1882 | 24705 | 100000 | 1635294 | 25294
2026-06-25 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 1 | 294 | 1294 | 4941 | 101176 | 1117
2026-06-26 | story | FAL-23 | 2.3 | Notify the customer | claude-sonnet-5 | claude-sonnet-5 | 14 | 1888 | 24720 | 100000 | 1635296 | 25296
2026-06-26 | ops | merges, promotions & deploys |  |  | claude-haiku-4-5-20251001 | claude-haiku-4-5 | 49 | 304 | 1304 | 4956 | 101216 | 1172

## Project Timeline
Project timeline
Started 2026-01-05; completed 2026-06-26; 173 calendar days, 125 working days. From git history of the BMad artifacts and sprint status, the agents' sanctums and the token ledger.
Category | Name | Detail | Status | Started | Completed | Days | Source
project | falcon-portal | 125 working days | complete | 2026-01-05 | 2026-06-26 | 173 | summary
bmad stage | spec / PRD | _bmad-output/specs/SPEC.md |  | 2026-01-06 | 2026-01-08 | 3 | git
bmad stage | architecture | _bmad-output/planning-artifacts/architecture/falcon/ARCHITECTURE-SPINE.md |  | 2026-01-12 | 2026-01-22 | 11 | git
bmad stage | UX design | _bmad-output/planning-artifacts/ux-design.md |  | 2026-01-19 | 2026-01-23 | 5 | git
bmad stage | epics & stories | _bmad-output/planning-artifacts/epics.md |  | 2026-01-26 | 2026-01-27 | 2 | git
bmad stage | sprint status | _bmad-output/implementation-artifacts/sprint-status.yaml |  | 2026-03-02 | 2026-06-26 | 117 | git
agent | agent-jules | 6 session logs |  | 2026-01-20 | 2026-02-20 | 32 | sanctum
agent | agent-scrooge | 4 session logs |  | 2026-01-20 | 2026-06-26 | 158 | sanctum
epic | epic-1 | 3 stories | done | 2026-03-02 | 2026-04-20 | 50 | git
story | 1-1-sign-in | epic-1 | done | 2026-03-02 | 2026-03-17 | 16 | git
story | 1-2-start-application | epic-1 | done | 2026-03-18 | 2026-04-02 | 16 | git
story | 1-3-upload-documents | epic-1 | done | 2026-04-03 | 2026-04-20 | 18 | git
epic | epic-2 | 3 stories | done | 2026-04-21 | 2026-06-26 | 67 | git
story | 2-1-review-queue | epic-2 | done | 2026-04-21 | 2026-05-12 | 22 | git
story | 2-2-approve-or-reject | epic-2 | done | 2026-05-13 | 2026-06-03 | 22 | git
story | 2-3-notify-customer | epic-2 | done | 2026-06-04 | 2026-06-26 | 23 | git

## Sources & Gaps
Sources, assumptions and gaps
Price basis
Azure Retail Prices API list prices (pay-as-you-go, no discounts), region uaenorth, USD, fetched 2026-09-28.
Rate card: Synthetic sample rates, not a real rate card, updated 2026-09-28.
Claude API list prices from https://platform.claude.com/docs/en/about-claude/pricing, read 2026-09-28, USD per million tokens. Claude Code on a subscription is billed per seat: this is the API-equivalent cost.
Horizon: 5 years of run after go-live, run costs rising 3% a year.
Gaps: not priced and not in any total
Disaster recovery: the spine does not say whether Prod has a second region.
Azure SQL backup retention beyond the default is not stated.
Assumptions and owner statements (not from the BMad artifacts)
Dev / Document storage: assumption: 50 GB of test documents
Test / Document storage: assumption: 50 GB of test documents
Team / Project Manager: owner: Delivery Manager, 2026-09-28
Team / Solution Architect: owner: Delivery Manager, 2026-09-28
Team / QA Engineer: owner: Delivery Manager, 2026-09-28
Other / Penetration test: owner: Security Lead, 2026-09-28
Other / GitHub Enterprise seats (12 months): assumption: 7 seats at list price
Run cost / Azure support plan (Standard): assumption: Standard support at list price
Run cost / GitHub Enterprise seats (4 for support): assumption: 4 seats at list price
Support / Developer: owner: Delivery Manager, 2026-09-28
Support / DevOps Engineer: owner: Delivery Manager, 2026-09-28
Support / QA Engineer: owner: Delivery Manager, 2026-09-28
Phase budget / governance (Jules): owner: Delivery Manager (synthetic), 2026-09-28
Phase budget / diagrams & design docs (Leonardo): owner: Delivery Manager (synthetic), 2026-09-28
Phase budget / test design: owner: Delivery Manager (synthetic), 2026-09-28
Stamp: built 2026-09-28T14:45:51; sha256 of each cited file
_bmad-output/planning-artifacts/architecture/falcon/ARCHITECTURE-SPINE.md 888bd47cdcac
_bmad-output/planning-artifacts/epics.md 68f432fd10b0
_bmad-output/specs/SPEC.md 13119f5f0756
token_usage/claude_usage.csv a04b88ac9faf
claude-prices.json 0dcde61aa110
token_usage/project_timeline.csv 08bf946524c1
token_usage/claude_usage_daily.csv f12be0ce39fb